## Overview
Computer Vision: From Foundations to Frontier
20-Chapter Book — 8-Week Writing Plan
Author | Milan Amrut Joshi
Start date | 2026-05-01 (Fri)
Target words/chapter | ~3,000
Total target words | 61500
Working days | 6
Hours/day | 3 (writing + code)
Buffer week | Week 10 (revision sprint)
Weekly Summary
Week | Dates | Chapters | Target Words | Difficulty | Notes
Week 0 | May 01 – May 07 | — | — | — | Pre-launch: repo, dataset, template
Week 1 | May 08 – May 14 | Ch1, Ch2 | 5800 | 1.0/5 | Foundations warm-up — fast wins
Week 2 | May 15 – May 21 | Ch3, Ch4 | 6200 | 2.5/5 | Geometry-heavy week — figures matter
Week 3 | May 22 – May 28 | Ch5, Ch6 | 6200 | 2.0/5 | CNN core + training tricks
Week 4 | May 29 – Jun 04 | Ch7, Ch8 | 6500 | 3.0/5 | Detection + segmentation. Mid-book consistency pass
Week 5 | Jun 05 – Jun 11 | Ch9, Ch10 | 6200 | 4.0/5 | ViTs + self-supervised (DINOv3)
Week 6 | Jun 12 – Jun 18 | Ch11, Ch12, Ch13 | 9500 | 3.7/5 | Hardest chapter (Diffusion) lands here
Week 7 | Jun 19 – Jun 25 | Ch14, Ch15, Ch16 | 9000 | 4.0/5 | Multimodal frontier + 3D Gaussian Splatting
Week 8 | Jun 26 – Jul 02 | Ch17, Ch18, Ch19, Ch20 | 12100 | 3.8/5 | VLA + Domains + Edge + MLOps + cross-pass

## Chapter Plan
Chapter Plan — All 20 Chapters
# | Chapter Title | Week | Target Words | Difficulty (1-5) | Hands-On Project | Status | Actual Words
1 | The 2026 Computer Vision Landscape | Week 1 | 2800 | 1 | Mental-model diagram + framework benchmark | Not started | 0
2 | Image Fundamentals and Pixel-Level Operations | Week 1 | 3000 | 1 | Document-cleanup preprocessor (OpenCV) | Not started | 0
3 | Classical Feature Engineering: SIFT, ORB, Geometry | Week 2 | 3000 | 2 | Multi-image panorama + logo detector | Not started | 0
4 | Camera Geometry, Calibration, and Stereo Vision | Week 2 | 3200 | 3 | Webcam calibration + StereoSGBM depth map | Not started | 0
5 | CNNs: From LeNet to ConvNeXt | Week 3 | 3200 | 2 | ResNet-18 from scratch on CIFAR-10 | Not started | 0
6 | Training Modern Vision Models in Practice | Week 3 | 3000 | 2 | Beat a timm baseline with training tricks | Not started | 0
7 | Object Detection: R-CNN to YOLO26 and DETR | Week 4 | 3300 | 3 | YOLO26 vs RT-DETR on Roboflow dataset | Not started | 0
8 | Image Segmentation: U-Net to SAM 3 + Grounding DINO | Week 4 | 3200 | 3 | Zero-shot Gradio segmentation app | Not started | 0
9 | Vision Transformers and Hybrid Architectures | Week 5 | 3200 | 4 | ViT vs ResNet attention/CAM comparison | Not started | 0
10 | Self-Supervised Vision: SimCLR to DINOv3 | Week 5 | 3000 | 4 | Frozen DINOv3 backbone for downstream seg | Not started | 0
11 | CLIP and Vision-Language Pretraining | Week 6 | 2800 | 3 | CLIP + FAISS photo search app | Not started | 0
12 | Generative Vision: GANs, VAEs, Diffusion Era | Week 6 | 3500 | 5 | SDXL LoRA fine-tune + ControlNet chain | Not started | 0
13 | Vision-Language Models: The Multimodal Stack | Week 6 | 3200 | 3 | Claude Vision + Qwen2.5-VL doc Q&A | Not started | 0
14 | Document AI and Visual Agents | Week 7 | 2800 | 3 | Invoice extraction + browser-control agent | Not started | 0
15 | Video Understanding: Action, Tracking, VideoMAE | Week 7 | 3000 | 4 | Sports-analytics pipeline (detect+track+count) | Not started | 0
16 | 3D Vision: Depth, NeRF, Gaussian Splatting | Week 7 | 3200 | 5 | Phone-capture to 3DGS fly-through | Not started | 0
17 | Vision-Language-Action Models for Robotics | Week 8 | 3300 | 5 | OpenVLA simulation + attention viz | Not started | 0
18 | Domain-Specific Vision: Medical, AV, Geospatial, Agri | Week 8 | 3000 | 3 | MONAI chest-X-ray + BEV toy example | Not started | 0
19 | Optimization and Edge Deployment | Week 8 | 2800 | 4 | YOLO26 INT8 → TensorRT → Jetson Orin Nano | Not started | 0
20 | MLOps, Responsible AI, and the Future of CV | Week 8 | 3000 | 3 | End-to-end production capstone | Not started | 0
| TOTAL |  | 61500 |  |  |  | 0
| PROGRESS |  | 0%

## Daily Schedule
Daily Writing Schedule (Mon–Sat, 6 days/week)
Day # | Date | Week | Day | Chapter | Activity | Hours | Done?
1 | 2026-05-01 | Week 0 | Fri | — | Set up GitHub repo: chapters/, notebooks/, figures/, case-studies/ | 2
2 | 2026-05-02 | Week 0 | Sat | — | Pick running case-study dataset (Roboflow 100 + EY domain) | 2
3 | 2026-05-04 | Week 0 | Mon | — | Draft chapter template (intro→theory→code→production→exercises→refs) | 2
4 | 2026-05-05 | Week 0 | Tue | — | Block daily writing window on calendar; install reference manager | 1
5 | 2026-05-06 | Week 0 | Wed | — | Read MIT visionbook + Stanford CS231n 2026 syllabus | 3
6 | 2026-05-07 | Week 0 | Thu | — | Snapshot dependency lockfile (requirements.txt, conda env) | 2
7 | 2026-05-08 | Week 1 | Fri | Ch1 | Ch1: outline + draft sections 1-3 (history, eras, pipeline) | 3
8 | 2026-05-09 | Week 1 | Sat | Ch1 | Ch1: draft sections 4-6 + framework comparison table | 3
9 | 2026-05-11 | Week 1 | Mon | Ch1 | Ch1: case-study introduction + figures + edit pass | 3
10 | 2026-05-12 | Week 1 | Tue | Ch2 | Ch2: draft pixel/color spaces + convolution sections | 3
11 | 2026-05-13 | Week 1 | Wed | Ch2 | Ch2: edge detection + morphology + thresholding | 3
12 | 2026-05-14 | Week 1 | Thu | Ch2 | Ch2: document-cleanup preprocessor notebook + edit | 3
13 | 2026-05-15 | Week 2 | Fri | Ch3 | Ch3: SIFT/ORB/BRIEF descriptors + matching theory | 3
14 | 2026-05-16 | Week 2 | Sat | Ch3 | Ch3: RANSAC + homography + Hough transforms | 3
15 | 2026-05-18 | Week 2 | Mon | Ch3 | Ch3: panorama + logo detector notebook | 3
16 | 2026-05-19 | Week 2 | Tue | Ch4 | Ch4: pinhole/fisheye models + intrinsics/extrinsics math | 3
17 | 2026-05-20 | Week 2 | Wed | Ch4 | Ch4: calibration + epipolar geometry + figures | 3
18 | 2026-05-21 | Week 2 | Thu | Ch4 | Ch4: webcam calibration + StereoSGBM notebook | 3
19 | 2026-05-22 | Week 3 | Fri | Ch5 | Ch5: implement ResNet-18 from scratch first, then write around it | 3
20 | 2026-05-23 | Week 3 | Sat | Ch5 | Ch5: CNN family-tree narrative (LeNet→ConvNeXt) | 3
21 | 2026-05-25 | Week 3 | Mon | Ch5 | Ch5: CIFAR-10 reproduction + edit + figures | 3
22 | 2026-05-26 | Week 3 | Tue | Ch6 | Ch6: data loaders + Albumentations + mixup/cutmix | 3
23 | 2026-05-27 | Week 3 | Wed | Ch6 | Ch6: optimizers + schedulers + AMP + Lightning | 3
24 | 2026-05-28 | Week 3 | Thu | Ch6 | Ch6: timm baseline-beating notebook + W&B integration | 3
25 | 2026-05-29 | Week 4 | Fri | Ch7 | Ch7: two-stage detectors narrative (R-CNN family) | 3
26 | 2026-05-30 | Week 4 | Sat | Ch7 | Ch7: YOLO evolution + DETR/RT-DETR + mAP/IoU | 3
27 | 2026-06-01 | Week 4 | Mon | Ch7 | Ch7: YOLO26 vs RT-DETR benchmark notebook | 3
28 | 2026-06-02 | Week 4 | Tue | Ch8 | Ch8: U-Net/DeepLab/Mask R-CNN narrative | 3
29 | 2026-06-03 | Week 4 | Wed | Ch8 | Ch8: SAM 3 + Grounding DINO architecture deep-dive | 3
30 | 2026-06-04 | Week 4 | Thu | Ch8 | Ch8: Gradio app + mid-book consistency pass | 4
31 | 2026-06-05 | Week 5 | Fri | Ch9 | Ch9: attention from scratch + ViT walkthrough | 3
32 | 2026-06-06 | Week 5 | Sat | Ch9 | Ch9: Swin/MaxViT/Mamba-Vision + when ViT wins/loses | 3
33 | 2026-06-08 | Week 5 | Mon | Ch9 | Ch9: ViT-Small ImageNette + attention-map figures | 3
34 | 2026-06-09 | Week 5 | Tue | Ch10 | Ch10: contrastive (SimCLR/MoCo/BYOL) narrative | 3
35 | 2026-06-10 | Week 5 | Wed | Ch10 | Ch10: MAE + DINO/v2/v3 + frozen-backbone story | 3
36 | 2026-06-11 | Week 5 | Thu | Ch10 | Ch10: DINOv3 frozen-backbone seg notebook | 3
37 | 2026-06-12 | Week 6 | Fri | Ch11 | Ch11: CLIP/SigLIP/EVA-CLIP + retrieval theory | 3
38 | 2026-06-13 | Week 6 | Sat | Ch11 | Ch11: photo search app (CLIP + FAISS) + prompt engineering | 3
39 | 2026-06-15 | Week 6 | Mon | Ch12 | Ch12: GAN/VAE narrative + diffusion DDPM math | 4
40 | 2026-06-16 | Week 6 | Tue | Ch12 | Ch12: SD 3.5/Flux/SDXL/ControlNet + LoRA fine-tune notebook | 4
41 | 2026-06-17 | Week 6 | Wed | Ch13 | Ch13: VLM anatomy + LLaVA/Qwen-VL/Florence-3 + Claude/GPT-4o/Gemini | 3
42 | 2026-06-18 | Week 6 | Thu | Ch13 | Ch13: Claude Vision doc Q&A + Qwen2.5-VL fallback notebook | 3
43 | 2026-06-19 | Week 7 | Fri | Ch14 | Ch14: OCR/layout (PaddleOCR/Donut/LayoutLM) + structured-output VLMs | 3
44 | 2026-06-20 | Week 7 | Sat | Ch14 | Ch14: visual agent loop + invoice + browser-agent notebook | 3
45 | 2026-06-22 | Week 7 | Mon | Ch15 | Ch15: optical flow + 3D CNNs + VideoMAE narrative | 3
46 | 2026-06-23 | Week 7 | Tue | Ch15 | Ch15: tracking (SORT→ByteTrack→SAM 2) + sports-analytics demo | 3
47 | 2026-06-24 | Week 7 | Wed | Ch16 | Ch16: depth + point clouds + COLMAP + NeRF lineage | 4
48 | 2026-06-25 | Week 7 | Thu | Ch16 | Ch16: 3DGS + Nerfstudio + phone-capture fly-through notebook | 4
49 | 2026-06-26 | Week 8 | Fri | Ch17 | Ch17: VLA paradigm + RT-2/OpenVLA/π0/Helix narrative | 4
50 | 2026-06-27 | Week 8 | Sat | Ch17 | Ch17: OpenVLA simulation + attention viz notebook | 4
51 | 2026-06-29 | Week 8 | Mon | Ch18 | Ch18: Medical (MONAI) + AV (BEV) + Geospatial + Agriculture | 4
52 | 2026-06-30 | Week 8 | Tue | Ch19 | Ch19: quantization + ONNX/TensorRT/CoreML + Jetson benchmark | 4
53 | 2026-07-01 | Week 8 | Wed | Ch20 | Ch20: MLOps + responsible AI + future + capstone integration | 4
54 | 2026-07-02 | Week 8 | Thu | — | Cross-chapter pass: forward refs, dedup, transitions, figure polish | 5

## Daily Routine
Daily Routine That Makes 8 Weeks Possible
Time | Activity | Why
Morning (90 min) | Drafting prose for current chapter | No research, no rabbit holes — pure output. Highest energy hours.
Midday (60 min) | Code / notebook for current chapter | Code first, prose around it. Notebook drives the explanation.
Evening (30 min) | Outline tomorrow + collect 2-3 references | Avoid blank-page friction at start of next session.
Weekly | Saturday is buffer / catch-up | Sunday off. Avoid burnout.
Mid-book (end Week 4) | Half-day consistency pass on Ch 1-8 | Catch voice drift early; build cross-references list.
Weekly check | Update Chapter Plan status + actual words | Tracks momentum honestly.

## Risks & Mitigations
Risks and Mitigations
Risk | Mitigation | Trigger
Hardest chapters (Diffusion Ch12, VLA Ch17, 3DGS Ch16) bog down whole plan | Schedule them in peak weeks (5-7), not the last week. Pre-research one week ahead. | When draft progress for these chapters falls behind by >1 day
Code breaks across library upgrades | Pin every dependency in a per-chapter requirements.txt; snapshot Colab-compatible env | Any "it worked yesterday" moment
"Just one more reference" rabbit hole | Hard-cap research at 30 min/day per chapter; missing items become footnotes for revision pass | When research time exceeds writing time on any day
Energy dip in Week 5 (statistically common) | Pre-book a no-meetings, single-coffee-shop writing day to break the slump | Two consecutive low-output days
Voice / tone drift across chapters | Mid-book consistency pass at end of Week 4 (built into schedule) | When re-reading earlier chapters feels like another author wrote them
VLA / SAM 3 / SD 3.5 lib changes mid-writing | Lock model versions; note "as of Apr 2026" inline so updates are easy | Major release announcement during writing period
Underestimating revision time | Reserve full Week 9 buffer for revision + reviewer feedback | When draft completes but reviewers find structural issues

## Word Tracker
Daily Word Count Tracker
Date | Day | Words Drafted | Cumulative | Notes | Goal | 61500
2026-05-01 | Fri |  | 0 |  | Cumulative % | 0%
2026-05-02 | Sat |  | 0
2026-05-04 | Mon |  | 0
2026-05-05 | Tue |  | 0
2026-05-06 | Wed |  | 0
2026-05-07 | Thu |  | 0
2026-05-08 | Fri |  | 0
2026-05-09 | Sat |  | 0
2026-05-11 | Mon |  | 0
2026-05-12 | Tue |  | 0
2026-05-13 | Wed |  | 0
2026-05-14 | Thu |  | 0
2026-05-15 | Fri |  | 0
2026-05-16 | Sat |  | 0
2026-05-18 | Mon |  | 0
2026-05-19 | Tue |  | 0
2026-05-20 | Wed |  | 0
2026-05-21 | Thu |  | 0
2026-05-22 | Fri |  | 0
2026-05-23 | Sat |  | 0
2026-05-25 | Mon |  | 0
2026-05-26 | Tue |  | 0
2026-05-27 | Wed |  | 0
2026-05-28 | Thu |  | 0
2026-05-29 | Fri |  | 0
2026-05-30 | Sat |  | 0
2026-06-01 | Mon |  | 0
2026-06-02 | Tue |  | 0
2026-06-03 | Wed |  | 0
2026-06-04 | Thu |  | 0
2026-06-05 | Fri |  | 0
2026-06-06 | Sat |  | 0
2026-06-08 | Mon |  | 0
2026-06-09 | Tue |  | 0
2026-06-10 | Wed |  | 0
2026-06-11 | Thu |  | 0
2026-06-12 | Fri |  | 0
2026-06-13 | Sat |  | 0
2026-06-15 | Mon |  | 0
2026-06-16 | Tue |  | 0
2026-06-17 | Wed |  | 0
2026-06-18 | Thu |  | 0
2026-06-19 | Fri |  | 0
2026-06-20 | Sat |  | 0
2026-06-22 | Mon |  | 0
2026-06-23 | Tue |  | 0
2026-06-24 | Wed |  | 0
2026-06-25 | Thu |  | 0
2026-06-26 | Fri |  | 0
2026-06-27 | Sat |  | 0
2026-06-29 | Mon |  | 0
2026-06-30 | Tue |  | 0
2026-07-01 | Wed |  | 0
2026-07-02 | Thu |  | 0